## Sheet1
Max MRS Project Activity Report
Slno | Activity Description | P | Owner | Planned/Budgeted Hours | Expected Date of Closure | Start Date | Actual Efforts in Hours | End Date | Status | MON | TUE | WED | THU | FRI | SAT | Remarks
1 | Max-MRS Documentation | [7 empty] | Completed
2 | Max- MRS Class Diagram | [7 empty] | Completed
3 | Max-MRS Screen design | [7 empty] | Completed
4 | Max MRS Data base design | [7 empty] | Completed
5 | Splitting projects into two Individual projects | [7 empty] | Completed
6 | Splitting data base | [7 empty] | Completed
7 | Controllers in MVC for both projects | [7 empty] | Completed
8 | Add Client Employeess to Database | [7 empty] | Completed
9 | View & Update of Client Employees | [7 empty] | Completed
10 | Add Clients To database | [7 empty] | Completed
11 | View & Update of Clients | [7 empty] | Completed
12 | Add Doctors | [7 empty] | Completed
13 | View & Update of Doctors
14 | Adding Doctor Groups | [7 empty] | completed
15 | Employee(Update) |  |  | 2hr | 2018-02-12 | 2018-02-12 |  |  | in progess
16 | Employee(Documents Upload) |  |  | 3hr | 2018-02-12 | 2018-02-12 |  |  | not yet started
17 | Employee (Documents View) |  |  | 1hr | 2018-02-13 | 2018-02-12 |  |  | not yet started
18 | Employee PayScale |  |  | 1hr | 2018-02-14 | 2018-02-14 |  |  | not yet started
19 | Employee PayScale Update |  |  | 1hr | 2018-02-14 | 2018-02-14 |  |  | not yet started